## WBS
IITP 큐브리드 이관 도구(MiT) WBS (Draft version)
참고사항
1. 연구개발 계획서에 있는 것처럼 QA 일정이 매년(11, 12월) 마다 있어야 한다면 초과되는 일정은 4차년도(2024년)로 이동 요청 필요하다고 판단됩니다.
2. 1차년도(RDB to GDB)는 2차년도 보다 개발 비중이 크다고 판단되지만 연구개발 계획서에 맞게 맞추면서 Overphase 일정이 예상됩니다.
[5 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | 비고사항
[5 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
IITP 큐브리드
2차년도 (2022.01.01 ~ 2022.12.31)
RDB to GDB
Connection
RDB 연결 설정 | bar: Jan W2 to Jan W4
연결 테스트 기능 | bar: Jan W4 to Feb W1
Transformation
메타데이터 획득 | bar: Feb W1 to Feb W2
메타데이터를 모델로 변환 | bar: Feb W2 to Mar W4
모델 변환 시각화 | bar: Mar W4 to May W4
Vertex 속성 설정 | bar: June W1 to June W3
Vertex 속성 Skip 설정 | bar: June W3 to June W4
Edge 속성 설정 | bar: July W1 to July W3
Edge 속성 Skip 설정 | bar: July W3 to July W4
|  |  |  | Edge 연결 변경 설정 | [48 empty] | 가능하다면 최적화/안정화, 추가 기능 개발 (2024년)로 이동 건의 | bar: August W1 to September W4
|  |  |  | Edge 추천 기능 | [48 empty] | 가능하다면 최적화/안정화, 추가 기능 개발 (2024년)로 이동 건의 | bar: September W3 to October W1
Migration
Export Data | bar: October W1 to November W4
Import Data | bar: October W1 to November W4
|  |  |  | Export file for GDB | [48 empty] | 가능하다면 최적화/안정화, 추가 기능 개발 (2024년)로 이동 건의 | bar: November W3 to December W4
|  |  |  | 증분 이관 | [48 empty] | 가능하다면 최적화/안정화, 추가 기능 개발 (2024년)로 이동 건의 | bar: October W1 to December W4
Multi thread support | bar: October W1 to November W4
Export CMT Script | bar: December W1 to December W4
Interface
CLI 제공 | bar: December W2 to December W4
GUI 제공 | bar: Jan W1 to Jan W3; October W1 to October W4
RDB interface | bar: Feb W1 to Feb W2; October W1 to October W4
GDB interface | bar: October W1 to October W4
Result
이관 Summary 기능 | bar: November W1 to November W4
에러 로그 기능 | bar: November W1 to December W4
[5 empty] | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
[5 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
3차년도 (2023.01.01 ~ 2023.12.31)
GDB to RDB
Connection
GDB 연결 설정 | bar: Jan W2 to Jan W4
연결 테스트 기능 | bar: Jan W4 to Feb W1
Transformation
GDB 질의 입력 | bar: Feb W2 to Apr W1
질의 결과 반환 | bar: Apr W1 to June W4
Migration
Import Data | bar: July W1 to August W4
Export Data | bar: July W1 to August W4
Export file for RDB | bar: September W1 to September W4
Multi thread support | bar: July W1 to August W4
Export CMT Script | bar: October W1 to October W4
Interface
CLI 제공 | bar: October W2 to October W4
GUI 제공 | bar: Jan W1 to Jan W3
RDB interface | bar: July W1 to July W4
GDB interface | bar: Mar W1 to Mar W4; July W1 to July W4
Result
이관 Summary 기능 | bar: November W1 to November W4
에러 로그 기능 | bar: November W1 to December W4